## Dashboard
City of Little Rock CDBG-DR Dashboard
DR-4698 Tornado Recovery ¦ Quarter Ending June 30, 2026
| Grant Award | Expended | Remaining | Percent Expended
| 20895000 | 228005.81 | 20666994.19 | 1.091%

## Actuals vs Projections
Actuals vs. Projections by Year
Year | Projected Expenditures ($) | Actual Expenditures ($) | Variance ($) | Actual as % of Projection | Status
2025 | 85659 | 102283.9 | 16624.9 | 119.4% | On Track
2026 | 4908664.8087 | 212993.74 | -4695671.0687 | 4.339% | Below Pace
2027 | 5954555.1955 | 0 | -5954555.1955 | 0% | Future
2028 | 4982979.6787 | 0 | -4982979.6787 | 0% | Future
2029 | 2566209.2906 | 0 | -2566209.2906 | 0% | Future
2030-Apr 2031 | 1636158.7114 | 0 | -1636158.7114 | 0% | Future
|  | 0 |  |  |  |  | 2031 | 1542716.1 | 0
Total | 20134226.6851 | 315277.64 | -19818949.0451 | 1.566% | Life of Grant
Projected Expenditures by Activity and Year
Note: Annual projections are intentionally set below 100% of the total budget to provide a contingency buffer.
Activity | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 - Apr 2031
Administration | 85659 | 165041 | 166616.4731 | 168207.6379 | 169814.7142 | 233583.8152
Planning | 0 | 34019.27 | 34606.8924 | 35209.051 | 35826.1944 | 30788.6705
New Affordable Housing | 0 | 858837.0938 | 1696424.2809 | 1989385.6736 | 1059090.3575 | 692980.7404
Homeowner Rehabilitation | 0 | 2499750 | 1147612.5 | 463635.45 | 234135.9022 | 141886.3568
Homebuyer Assistance | 0 | 155900 | 360000 | 225000 | 150000 | 90000
Infrastructure | 0 | 505900 | 1000000 | 741415.3769 | 120489.9151 | 40163.305
Mitigation | 0 | 656417.445 | 908695.0491 | 594526.4894 | 406252.2071 | 256755.8236
Economic Revitalization | 0 | 16400 | 407800 | 607800 | 307800 | 150000
Public Services | 0 | 16400 | 232800 | 157800 | 82800 | 0
Total | 85659 | 4908664.8087 | 5954555.1955 | 4982979.6787 | 2566209.2906 | 1636158.7114
Actual Expenditures by Activity — Selected Year
Selected Year | 2025
Activity | Annual Projection ($) | Actual ($) | Variance ($)
Administration | 85659 | 84433.9 | -1225.1
Planning | 0 | 17850 | 17850
New Affordable Housing | 0 | 0 | 0
Homeowner Rehabilitation | 0 | 0 | 0
Homebuyer Assistance | 0 | 0 | 0
Infrastructure | 0 | 0 | 0
Mitigation | 0 | 0 | 0
Economic Revitalization | 0 | 0 | 0
Public Services | 0 | 0 | 0
[7 empty] | Year | Cumulative Projection | Cumulative Actual
[7 empty] | 2025 | 85659 | 102283.9
[7 empty] | 2026 | 4994323.8087 | 315277.64
[7 empty] | 2027 | 10948879.0043 | 315277.64
[7 empty] | 2028 | 15931858.683 | 315277.64
[7 empty] | 2029 | 18498067.9736 | 315277.64
[7 empty] | 2030 | 20134226.6851 | 315277.64
[7 empty] | 2031 | 20134226.6851 | 315277.64
Formulas:
Status = IF([Year]>YEAR(TODAY()),"Future",IF([Actual as % of Projection]>=0.9,"On Track",IF([Actual as % of Projection]>=0.7,"Watch","Below Pace")))

## Data & Outcomes
Data & Outcomes
Approved
Activity | Budget | Actual Expenditures | Applications / Projects Received | In Progress | Under Review | Awarded | Completed | Denied/Withdrawn | Remaining | % Expended
Administration | 1044750 | 102283.9 | [6 empty] | 942466.1 | 9.79%
Planning | 200000 | 18190.91 | 0 | 0 | 0 | 0 | 0 | 0 | 181809.09 | 9.095%
New Affordable Housing | 6500000 | 31465.5 | 2 | 0 | 0 | 0 | 0 | 0 | 6468534.5 | 0.4841%
Homeowner Rehabilitation | 4503250 | 20965.5 | 61 | 33 | 19 | 0 | 0 | 9 | 4482284.5 | 0.4656%
Homebuyer Assistance | 1000000 | 5900 | 1 | 0 | 0 | 1 | 0 | 0 | 994100 | 0.59%
Infrastructure | 2500000 | 16400 | 2 | 0 | 0 | 1 | 0 | 1 | 2483600 | 0.656%
Mitigation | 3147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3147000 | 0%
Economic Revitalization | 1500000 | 16400 | 0 | 0 | 0 | 0 | 0 | 0 | 1483600 | 1.093%
Public Services | 500000 | 16400 | 0 | 0 | 0 | 0 | 0 | 0 | 483600 | 3.28%
|  |  | Actuals | [6 empty] | Quarter End | Quarterly Expenditures | Cumulative Expenditures
ACTIVITY # | SOURCES | Budget | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 |  | 2025-12-31 | 102283.9 | 102283.9
G35DR25AD | Administration | 1044750 | 84433.9 | 105121.83 | 0 | 0 | 0 | 0 | 189555.73 | 2026-03-31 | 94317.18 | 196601.08
G35DR25PL | Planning | 200000 | 17850 | 340.91 | 0 | 0 | 0 | 0 | 18190.91 | 2026-06-30 | 118676.56 | 315277.64
G35DR25HO | New Affordable Housing | 6500000 | 0 | 31465.5 | 0 | 0 | 0 | 0 | 31465.5 | 2026-09-30 | 0 | 315277.64
G35DR25RH | Homeowner Rehabilitation | 4503250 | 0 | 20965.5 | 0 | 0 | 0 | 0 | 20965.5 | 2026-12-31 | 0 | 0
G35DR25HA | Homebuyer Assistance | 1000000 | 0 | 5900 | 0 | 0 | 0 | 0 | 5900 | 2027-03-31 | 0 | 0
G35DR25IN | Infrastructure | 2500000 | 0 | 16400 | 0 | 0 | 0 | 0 | 16400 | 2027-06-30 | 0 | 0
G35DR25MA | Mitigation | 3147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2027-09-30 | 0 | 0
G35DR25ER | Economic Revitalization | 1500000 | 0 | 16400 | 0 | 0 | 0 | 0 | 16400 | 2027-12-31 | 0 | 0
G35DR25PS | Public Services | 500000 | 0 | 16400 | 0 | 0 | 0 | 0 | 16400 | 2028-03-31 | 0 | 0
TOTAL | All Activities |  | 102283.9 | 212993.74 | 0 | 0 | 0 | 0 |  | 2028-06-30 | 0 | 0
[10 empty] | 2028-09-30 | 0 | 0
Planning |  |  | Actuals 2026: Infrastructure & Mitigation |  | 2028-12-31 | 0 | 0
Performance Measure | Projected | Actual | Actuals 2026: Performance Measure; Actuals 2027: Projected; Actuals 2028: Actual |  | 2029-03-31 | 0 | 0
Activity funds eligible for DREF (Ike Only) | N/A | 0 | Actuals 2026: # of public facilities; Actuals 2027: 2; Actuals 2028: 0 |  | 2029-06-30 | 0 | 0
# of community engagement meetings/events | 10 | 0 | Actuals 2026: # of Persons; Actuals 2027: 5365; Actuals 2028: 0 |  | 2029-09-30 | 0 | 0
# of Organizations or subrecipients assisted | N/A | 0 | [7 empty] | 2029-12-31 | 0 | 0
# of Plans or Planning Products | 1 | 0 | [7 empty] | 2030-03-31 | 0 | 0
[10 empty] | 2030-06-30 | 0 | 0
New Affordable Housing |  |  | Actuals 2026: Homeowner Rehabilitation |  | 2030-09-30 | 0 | 0
Performance Measure | Projected | Actual | Actuals 2026: Performance Measure; Actuals 2027: Projected; Actuals 2028: Actual |  | 2030-12-31 | 0 | 0
#Sites re-used | 1 | 0 | Actuals 2026: # ELI Households (0-30% AMI); Actuals 2027: 5; Actuals 2028: 0 |  | 2031-03-31 | 0 | 0
# ELI Households (0-30% AMI) | 1 | 0 | Actuals 2026: # of Properties; Actuals 2027: 18; Actuals 2028: 0 |  | 2031-06-30 | 0 | 0
# of Total Labor Hours | 10969 | 0 | Actuals 2026: # of Section 3 Labor Hours; Actuals 2027: 2714; Actuals 2028: 0
# of Section 3 Labor Hours | 2742 | 0 | Actuals 2026: # of Targeted Section 3 Labor Hours; Actuals 2027: 543; Actuals 2028: 0
# of Targeted Section 3 Labor Hours | 548 | 0 | Actuals 2026: # of Total Labor Hours; Actuals 2027: 10856; Actuals 2028: 0
# of Households | 12 | 0 | Actuals 2026: # of Households; Actuals 2027: 15; Actuals 2028: 0
# Owner Households | 12 | 0 | Actuals 2026: # Owner Households (95%); Actuals 2027: 15; Actuals 2028: 0
Homebuyer Assistance |  |  | Actuals 2026: Economic Revitalization
Performance Measure | Projected | Actual | Actuals 2026: Performance Measure; Actuals 2027: Projected; Actuals 2028: Actual
# of Households | 35 |  | Actuals 2026: # of Businesses; Actuals 2027: 40.9; Actuals 2028: 0
|  |  |  | # of Permanent Jobs Created | 5 | 0
Public Services |  |  | Actuals 2026: # of Permanent Jobs Retained; Actuals 2027: 40; Actuals 2028: 0
Performance Measure | Projected | Actual
Projected Beneficiaries | 5365 | 0
# of facilities with mitigation measures (other than elevation) | 2 | 0

## Program Status
Program Status Dashboard
Program | Budget | Expended | Remaining | % Expended | Applications / Projects | Approved / Awarded | Completed
Administration | 1044750 | 102283.9 | 942466.1 | 9.79%
Planning | 200000 | 18190.91 | 181809.09 | 9.095% | 0 | 0 | 0
New Affordable Housing | 6500000 | 31465.5 | 6468534.5 | 0.4841% | 2 | 0 | 0
Homeowner Rehabilitation | 4503250 | 20965.5 | 4482284.5 | 0.4656% | 61 | 0 | 0
Homebuyer Assistance | 1000000 | 5900 | 994100 | 0.59% | 1 | 1 | 0 | Program | Budget | Expended
Infrastructure | 2500000 | 16400 | 2483600 | 0.656% | 2 | 1 | 0 | Administration | 1044750 | 102283.9
Mitigation | 3147000 | 0 | 3147000 | 0% | 0 | 0 | 0 | Planning | 200000 | 18190.91
Economic Revitalization | 1500000 | 16400 | 1483600 | 1.093% | 0 | 0 | 0 | New Affordable Housing | 6500000 | 31465.5
Public Services | 500000 | 16400 | 483600 | 3.28% | 0 | 0 | 0 | Homeowner Rehabilitation | 4503250 | 20965.5
[8 empty] | Homebuyer Assistance | 1000000 | 5900
[8 empty] | Infrastructure | 2500000 | 16400
[8 empty] | Mitigation | 3147000 | 0
[8 empty] | Economic Revitalization | 1500000 | 16400
[8 empty] | Public Services | 500000 | 16400
[8 empty] | Program | Applications / Projects | Approved / Awarded | Completed
[8 empty] | Administration | 0 | 0 | 0
[8 empty] | Planning | 0 | 0 | 0
[8 empty] | New Affordable Housing | 2 | 0 | 0
[8 empty] | Homeowner Rehabilitation | 61 | 0 | 0
[8 empty] | Homebuyer Assistance | 1 | 1 | 0
[8 empty] | Infrastructure | 2 | 1 | 0
[8 empty] | Mitigation | 0 | 0 | 0
[8 empty] | Economic Revitalization | 0 | 0 | 0
[8 empty] | Public Services | 0 | 0 | 0

## Quarterly Update Visual
Quarterly Update and Visual Report
Quarter End | Quarterly Expenditures | Cumulative Expenditures
2025-12-31 | 102283.9 | 102283.9
2026-03-31 | 94317.18 | 196601.08
2026-06-30 | 118676.56 | 315277.64
2026-09-30 | 0 | 315277.64
Program | Applications / Projects | Approved / Awarded | Completed | Actual Expenditures | % Expended
Administration | 0 | 0 | 0 | 102283.9 | 9.79%
Planning | 0 | 0 | 0 | 18190.91 | 9.095%
New Affordable Housing | 2 | 0 | 0 | 31465.5 | 0.4841%
Homeowner Rehabilitation | 61 | 0 | 0 | 20965.5 | 0.4656%
Homebuyer Assistance | 1 | 1 | 0 | 5900 | 0.59%
Infrastructure | 2 | 1 | 0 | 16400 | 0.656%
Mitigation | 0 | 0 | 0 | 0 | 0%
Economic Revitalization | 0 | 0 | 0 | 16400 | 1.093%
Public Services | 0 | 0 | 0 | 16400 | 3.28%